Section 03

## Academic Cycle: The 40-Session Macro-Structure

The BnB academic year is a precisely designed 40-session system bifurcated into two 20-session quarters, balancing skill scaffolding with applied production.

40 Total Sessions / Year

2 Quarters

20 Sessions / Quarter

45 min Per Session

2× Weekly (Tue & Fri)

2 Age Cohorts

| Phase | Period | Duration | Focus | Persons in Charge |
| --- | --- | --- | --- | --- |
| Summer Bridge (Diagnostic) | June 25–27, 2026 | 3 Days | Onboarding, baseline assessment, musicality & movement evaluation | All Coaches |
| Quarter 1 — Skill Scaffolding | July 7 – September 15, 2026 | 20 Sessions | Technical & psychological foundation building (music, theatre, English) | All Coaches |
| Quarter 2 — Applied Integration | September 18 – November 24, 2026 | 20 Sessions | Production-driven rehearsal, character specialization, show preparation | All Coaches |
| Showcase Assessment | November 28, 2026 | 1 Day | Live public performance — "Moana Jr." (Broadway Jr. licensed) | All Team |
| Next Semester Intake | December 1, 2026 | Announcement | Announcing 2027 semester show title (Frozen Jr. or Shrek Jr.) | Ellen & Rei |

Strategic Note — Semester 2 (2027)

The odd semester spans January 5 – May 28, 2027, culminating in a showtime on May 29. The 2027 Summer Class is scheduled June 24–26, maintaining the cyclical production-house rhythm established in 2026.