Section 07

## Operational Timeline 2026–2027

The operational roadmap covers every key milestone from first social media post through to the 2027 showcase — a fully planned institutional calendar.

2026

May 14, 2026

Instagram Launch

PIC: Rei

Content pillars provided; posting every other day. Building awareness campaign begins with 9 educational posts followed by promotional content.

June 1, 2026

Open Registration

PIC: Ellen

Finalize fees and promo structure. Early bird admission period: June 1–30.

June 25–27, 2026

Summer Class

PIC: All Coaches

Trial class for student experience and content materials. Needs: fees & cost structure, minimum student count to start, 2-day materials including script.

July 7 – September 15, 2026

Quarter 1 — Skill Scaffolding

PIC: All Coaches

20 meetings across Music, Theatre, and English modules. Two sessions per week, Tuesdays and Fridays.

August 1, 2026

Broadway Jr. Script Licensing

PIC: Ellen

Moana Jr. (21+ performers) — 10-day processing for digital set. Physical materials shipped late September. MTI Shows licensing via mtishows.com.

September 18 – November 24, 2026

Quarter 2 — Applied Integration

PIC: All Coaches

20 meetings of full production rehearsal. Students work with physical scripts, develop characters, and prepare the complete Moana Jr. showcase.

November 28, 2026

SHOWCASE: Moana Jr.

PIC: All Team

Live public performance. Pending confirmation: venue, ticket pricing, and backstage team. Open auditions for cast, understudies, and backstage crew.

December 1, 2026

Next Semester Intake Announcement

PIC: Ellen & Rei

Announcing the next show title — candidates: Frozen Jr. (20+ performers) or Shrek the Musical Jr. (20+ performers).

2027

January 5 – May 28, 2027

Odd Semester

PIC: All Coaches

Full 20-week semester following same 40-session structure. Show TBD.

May 29, 2027

Showtime!

PIC: All Team

Second major showcase performance — 2027 semester culmination.

June 24–26, 2027

Summer Class 2027

PIC: All Coaches

Cycle repeats — onboarding and diagnostics for the next cohort.